## DO NOT DELETE
This template is an exclusive property of Mapua-Malayan Digital College and is protected under Republic Act No. 8293, also known as the Intellectual Property Code of the Philippines (IP Code). It is provided solely for educational purposes within this course. Students may use this template to complete their tasks but may not modify, distribute, sell, upload, or claim ownership of the template itself. Such actions constitute copyright infringement under Sections 172, 177, and 216 of the IP Code and may result in legal consequences. Unauthorized use beyond this course may result in legal or academic consequences. Additionally, students must comply with the Mapua-Malayan Digital College Student Handbook, particularly with the following provisions: * Offenses Related to MMDC IT: - Section 6.2 – Unauthorized copying of files - Section 6.8 – Extraction of protected, copyrighted, and/or confidential information by electronic means using MMDC IT infrastructure * Offenses Related to MMDC Admin, IT, and Operations: - Section 4.5 – Unauthorized collection or extraction of money, checks, or other instruments of monetary equivalent in connection with matters pertaining to MMDC Violations of these policies may result in disciplinary actions ranging from suspension to dismissal, in accordance with the Student Handbook. For permissions or inquiries, please contact MMDC-ISD at isd@mmdc.mcl.edu.ph.

## Effort Estimation
MO-IT101 - Computer Programming 1
Effort Estimation
GUIDE QUESTION | TASK | RESPONSE
What are the main tasks you need to do? (Insert additional rows if you have more than 10 tasks) | 1 | Visualization of requirements
| 2 | Plan the layout for employee information presentation
| 3 | Design a code structure for storing employee data
| 4 | Implement input for employee working hours
| 5 | Calculate total weekly hours worked
| 6 | Calculate gross weekly salary based on hours
| 7 | Apply basic deductions to compute net salary
| 8 | Display employee information with salary details
| 9 | Test and debug the code
| 10 | Document code and workflow
What do you need to know to accomplish these tasks? (Insert additional rows if you have more than 10 tasks) | 1 | Knowledge of required employee data (employee number, name, birthday)
| 2 | Basic UI/UX principles for table or console display
| 3 | Understanding of arrays, lists, or objects in Java
| 4 | Knowledge of reading user input and validating it
| 5 | Ability to sum multiple daily hour inputs
| 6 | Formula for hourly wage calculation
| 7 | Knowledge of deductions (tax, SSS, etc.)
| 8 | Combining data presentation and computed values
| 9 | Basic debugging techniques in Java
| 10 | Knowledge of documenting code and creating user guides
What additional help do you think you need to be able to do each task? (Insert additional rows if you have more than 10 tasks) | 1 | Access to sample employee data or dummy dataset
| 2 | Examples of simple UI design or presentation templates
| 3 | Examples of simple UI design or presentation templates
| 4 | Guidance on best input validation practices
| 5 | Sample formulas or pseudocode for calculating hours
| 6 | Clarification on overtime rules (if any)
| 7 | Examples of deduction formulas
| 8 | Sample formatted output for guidance
| 9 | Access to debugging tools or IDE features
| 10 | Template for documentation or reporting
Given the nature of the task, the knowledge you need, and any additional help you need, how long do you think it would it take you (in hours) to finish each task? (Insert additional rows if you have more than 10 tasks) | 1 | 5 hours Review project requirements and scope
| 2 | 6 hours Analyze payroll rules and government deduction
| 3 | 6 hours Design payroll system workflow
| 4 | 5 hours Create system visualization and wireframe
| 5 | 4 hours Prepare employee data structure
| 6 | 6 hours Implement attendance and timekeeping logic
| 7 | 5 hours Calculate hours worked
| 8 | 5 hours Compute gross salary
| 9 | 6 hours Compute net salary with deductions
| 10 | 7 hours Testing, debugging, and revisions
In this course, you are expected to dedicate 7.5 hours per week. Based on the total number of hours you estimated, how many weeks will you need to finish your outputs? | Based on the estimated total of 55 hours, I will need approximately 8 weeks to complete all required outputs while dedicating 7.5 hours per week, which aligns with the official project timeline in the Milestone 1 plan

## Project Plan Guide
MO-IT101 - Computer Programming 1
Project Plan Guide
Use the guide below to help you fill out this template
1 | Begin by filling out the general information section above.
2 | TASK # - Use whole numbers to specify main tasks (e.g., 1,2,3). If the task is considered a sub-task, advance the numbering using decimal points to still identify what the main task is (e.g., 1.1, 1.2, 1.3).
3 | TASK - Describe the task. Start tasks with verbs/action words to add specificity, e.g., List requirements instead of simply Requirements.
4 | DEPENDENCY - Identify the task which cannot be started unless a previous task has been completed. Leave this blank if there is no dependency.
5 | OWNER - Identify the person responsible for completing the task.
6 | START DATE & END DATE - Identify the planned start and end dates per task. The main task's start and end-date should be the start date of the first sub-task and the end date of the last sub-task. The last end date in your project plan should be within the submission dates indicated in your syllabus.
7 | STATUS - By default, all tasks start with a Not Started status. Change the status to In Progress if it's already being worked on and Completed once the task is done.
8 | ACTUAL START & END DATE - Specify the actual start and end dates per task. This allows you to identify whether you were able to adhere to your initial timelines and if you will be able to complete the rest of your tasks on time. If you see that you don't have sufficient time, you need to work with your team to decide on alternatives or adjustments.
9 | NOTES - Indicate any notes or reminders you may have for each task.

## Project Plan
w
MO-IT101 - Computer Programming 1
Project Plan
| TASK # | TASK | DEPENDENCY | OWNER | START DATE | END DATE | STATUS | ACTUAL START DATE | ACTUAL END DATE | NOTES
| 1 | Review and analyze project requirements |  |  |  |  | Completed
| 1.1 | Review project requirements |  | All members | 2026-01-05 | 2026-01-07 | Completed | 2026-01-05 | 2026-01-07
| 1.2 | Analyze payroll rules & deductions | 1.1 | All members | 2026-01-07 | 2026-01-10 | Completed | 2026-01-07 | 2026-01-10
| 1.3 | Define system scope & limitations | 1.2 | All members | 2026-01-08 | 2026-01-13 | Completed | 2026-01-08 | 2026-01-13
| 2 | Design payroll workflow and logic
| 2.1 | Draft payroll workflow | 1.3 | Princess Rey Ann Lene Romo | 2026-01-10 | 2026-01-16 | Completed
| 2.2 | Research attendance rules | 2.1 | Ivone Christel Trinidad | 2026-01-15 | 2026-01-19 | Completed
| 3 | Create system wireframes | 2.1 | Ephraim Elayda | 2026-01-18 | 2026-01-22 | Completed | 2026-01-09 | 2026-01-11
| 3.1 | Create system login wireframes | 2.1 | Ephraim Elayda | 2026-01-18 | 2026-01-22 | Completed | 2026-01-09 | 2026-01-11
| 3.2 | Create payroll interface wireframe | 3.1 | Ashley Mackenzie Ramos | 2026-01-21 | 2026-01-25 | Completed | 2026-01-09 | 2026-01-11
| 3.3 | Design payment confirmation layout | 3.2 | Ma. Irene Andrea Esguerra | 2026-01-24 | 2026-01-28 | Completed
| 4 | Prepare employee and attendance data structure | 1.3
| 4.1 | Prepare employee data structure | 1.3 | Princess Rey Ann Lene Romo | 2026-01-27 | 2026-01-31 | Not Started
| 4.2 | Validate employee records | 4.1 | Ivone Christel Trinidad | 2026-01-30 | 2026-02-03 | Not Started
| 5 | Develop attendance computation logic | 2.2
| 5.1 | Design attendance computation logic | 2.2 | Ephraim Elayda | 2026-02-02 | 2026-02-06 | Not Started
| 5.2 | Implement hours-worked computation | 5.1 | Ashley Mackenzie Ramos | 2026-02-05 | 2026-02-09 | Not Started
| 6 | Payroll Testing and Validation | 5.2
| 6.1 | Review salary computation formulas | 5.2 | Ma. Irene Andrea Esguerra | 2026-02-08 | 2026-02-12 | Not Started
| 6.2 | Design gross salary calculation | 6.1 | Princess Rey Ann Lene Romo | 2026-02-11 | 2026-02-15 | Not Started
| 6.3 | Design net salary calculation | 6.2 | Ivone Christel Trinidad | 2026-02-14 | 2026-02-18 | Not Started
| 6.4 | Integrate deduction logic | 6.3 | Ephraim Elayda | 2026-02-17 | 2026-02-21 | Not Started
| 7 | Verify and validate payroll results | 6.4
| 7.1 | Verify payroll computation results | 6.4 | Ashley Mackenzie Ramos | 2026-02-20 | 2026-02-24 | Not Started
| 7.2 | Document payroll computation process | 7.1 | Ma. Irene Andrea Esguerra | 2026-02-23 | 2026-02-27 | Not Started
| 8 | Testing and revision | 7.2
| 8.1 | Prepare test cases | 7.2 | Princess Rey Ann Lene Romo | 2026-02-26 | 2026-03-02 | Not Started
| 8.2 | Execute system testing | 8.1 | Ivone Christel Trinidad | 2026-03-01 | 2026-03-05 | Not Started
| 8.3 | Debug identified issues | 8.2 | Ephraim Elayda | 2026-03-04 | 2026-03-08 | Not Started
| 8.4 | Revise system based on feedback | 8.3 | Ashley Mackenzie Ramos | 2026-03-07 | 2026-03-11 | Not Started
| 9 | Finalization and submission | 8.4
| 9.1 | Prepare final documentation | 8.4 | Ma. Irene Andrea Esguerra | 2026-03-10 | 2026-03-14 | Not Started
| 9.2 | Conduct final system review | 9.1 | Princess Rey Ann Lene Romo | 2026-03-13 | 2026-03-17 | Not Started
| 9.3 | Final submission & presentation preparation | 9.2 | Ivone Christel Trinidad | 2026-03-16 | 2026-03-20 | Not Started